Sussex LNRS Working Group

Meeting Notes

Monday 15 January 2024, 11:00 to 13:00

Present

WSCC, ESCC, NE, NE, SWT, SDNPA, CJH Farm Advice/SE FWAG, MSDC, EA, BHCC, FC, WSCC, WayForward, HDC, HWOANB, CLM, ESCC, SxNP, Conservancy, FC, CLM, NFU, CLM, FC

Apologies

RDC, WDC, CBC

- Welcome, Introductions and Apologies

ESCC to Chair with support from WSCC.

- Minutes and matters arising

Minutes accepted and no matters arising.

ACTIONS from last meeting:

- To amend October 23 minutes in light of comments from NE. Completed.

- To amend ToR in light of discussion (in red in minutes) and circulate new draft. Completed. 3.1 is the correct version.

- Project Plan to be uploaded onto basecamp. Completed.

- To have regular agenda item updating progress and key timelines wrt WG. In update.

- To investigate whether the SAG and WG can be amalgamated or members of groups given access to both. Agreed to keep the two separate but there will be transparency.

- To add members to basecamp. Completed.

- To feedback preferences to RhinoBytes and confirm branding. Completed.

- Terms of Reference

Comments have been received and corrections made.

Discussion

Catchment partnerships are represented by SxNP and there is ongoing communication.

- General Update

Administration and governance: New NE LNRS lead for West Sussex.

Project planning: Broadly on track. Minor slippage on website building. The collation and analysis of strategies and plans delayed. The delays are minor inconveniences and there is no change in the spring/summer 2025 aspirations. Detailed budget figures added to the project plan.

Data and evidence: trends, pressures and threats piece ongoing.

Plans, policies and strategies: the piece is ongoing.

Regulations and guidance: BNG regulations and guidance published end of November and presented to the Local Authority Network. List on irreplaceable habitats which should be included within the LNRS. There are separate categories for saltmarsh but Sussex will be amalgamating them together. Guidance on data standards, mapping and planning advice is expected.

Species: reviewed guidance and attended Defra webinar. Some flexibility is allowed. A T&F group of main organisations across Sussex will be pulled together within the next week or two.

Marine: there is a national group on coastal RAs. One high level meeting so far. Sussex Bay recruited a Sussex Seascapes manager and will be encouraged to follow a similar process as set out in the LNRS.

Communications: focus on land managers/landowners. Draft engagement plan on costings developed. A date for the town and parish council briefing will be decided. Newsletter will be published by the end of January. Have presented to Downland Advisory Panel and East Sussex Environment Board.

- Update on Stakeholder Engagement

Discussion

This does not act as a supplement to other cluster work/initiatives but helps promote and amplify.

BOA statements are being used in the conversations with farmers/landowners, but additional work is ongoing to extract the relevant information from BOAs, as they are out of date.

The e-newsletter will be circulated to those who have registered interest and will also be shared with the LAs. Looking to include a registration link on the website.

- Update on plans and strategies

- Proposed approach to species

As covered in the general update.

- Next Steps

Representatives from BugLife and Species Recovery Trust will also be involved in T&F group.

Summary of actions from above:

- To check that the catchment partnerships and rivers trusts are happy with the arrangement.

- To double check the wording of paragraph 7.3 and send it for comment.

- Forestry Commission to sit on Task and Finish group.

- To look at creating a dedicated space on the website to signpost other engagement initiatives

- Have content available to be included within the LNRS video.

- To add signage as an option within question 7 of the public survey.

- To send the SurveyMonkey preview of the public survey for feedback.

- To check who can represent Wilder Horsham on the Task and Finish group for species work.

- To include a representative from the Sussex Bat Group on the Task and Finish group for species work.

- AOB

Request to release all minutes from previous LNRS group meetings onto new website. No objections.

Will need to be clear on the website and in communications work what is within and outside the scope of the LNRS.

Date of Next Meeting

Monday 19th February, 11:00 to 13:00.