Supporting Authorities Group Meeting

01/05/2024 14:00-15:30

This meeting was recorded.

Present

WSCC, RDC, A&WC, SxNP, RDC, ADC, NE, CDC, E&LC, HDC, ADC, E&LC, SDNPA, HDC, WSCC, ESCC, CBC, MDC, BHCC, ESCC, WayForward

No apologies.

WSCC chaired. No matters arising. Everything actioned in last meeting will be picked up on agenda.

Summary Actions:

| 1.2.d.i. | Send West Sussex documents to SDNPA. |
| --- | --- |
| 2.2.b. | Use their own channels to help WayForward with communications. |
| 2.2.c. | Share video and other related content to the youth cabinets. |
| 3 | Send any comments and feedback on the plans and strategies piece and to flag any new plans/strategies that can be added (no set date). |

Previous Actions:

| 1.2.c. | Put uploaded Defra webinars and slides onto Basecamp. |
| --- | --- |
| 2.1.f.i | Promote website via circulation of the link. |
|  | Follow up on the Google accessibility issue of the website. |
| 2.1.f.ii. | Introduce WayForward to the communications staff member of BHCC. |
| 3 | Complete tasks requested in slides. |
| 4.1.a. | Provide comments on ADC initial Local Plan document. |
| 4.1.b. | Arrange meeting with ADC. |

UPDATE

- Update: LNRS progress

  - Defra updates:-

- Mapping potential measures guidance published and being evaluated.

- Budget – more than enough to cover interim period.

  - Project plan: overall progress is good:-

- On track to deliver pre-consultation draft to SAG by December 2024.

- WBS 1 Preparatory work:

- All complete.

- Steps 1&3:

- APIB map complete but being finessed.

- Description chapter in development.

- Step 4

- Plans and strategies piece complete.

  - Capturing existing action:-

- Project mapping tool nearing completion. Waiting to be finalised.

  - Species:-

- T&FG has been formed.

- Species long list collated and will work to reduce to short list.

  - Marine:-

- Ongoing liaison with Sussex Bay on their Seascape Restoration Strategy. Will work closely to get high level marine priorities.

- National marine LNRS group dissolved.

  - Next steps:-

- Complete the description chapter.

- Continue to progress step 4.

- Continue with engagement (landowners, health/wellbeing, youth and businesses).

- Work on shortlisting species.

- Convene Technical Review Panel.

- Update: Engagement activites

  - Interim public survey results. 1260 responses as of this morning:-

- What do people love?

- Favourite habitats – woodland most mentioned.

- Favourite species – birds are by far the favourite group.

- What have people noticed?

- Negative changes:

- Decline in species abundance and condition/extent of habitats.

- Urbanisation/development, litter/pollution/pesticides, declining condition (poor management practices), other pressures.

- Positive changes:

- Work being done by LNRS partners to create/improve habitats.

- Changes in land management and practices.

- Action at home.

- Species:

- Loss in bird numbers, insects, hedgehogs, bats and amphibians.

- Increase in birds of prey and return of storks and butterflies.

- Increase in invasive species, including deer and urban foxes.

- Most people are concerned but ongoing work is a source of hope.

- What do people want to see?

- Habitats:

- Most mentioned – woodland, hedgerows, river catchment, meadows and marine.

- Species:

- Most mentioned – birds, hedgehogs, butterflies, insects and bees.

- Co-benefits:

- Most mentioned – clean air and water, and reduction in flood and storm impact. Just knowing that there is action for nature.

- Other themes:

- Thoughtful development, green corridors, working with farmers, joined up planning, local action enabled and better access.

  - Next steps:

- Upcoming public webinars in June. Educational and inspiring. Sourcing some case studies (e.g. B&H Albion, W2W and other community groups).

- Entering a big stage of communications to get messages out.

- Working with youth cabinets of Sussex to create engaging content. Aiming to create a younger person friendly version of the survey and send to schools.

- Upcoming farmer/landowner conversations in May/June.

- Update: Plans and Strategies

- Follow up: health/wellbeing LNRS workshop

Online event in February 2024 to discuss the LNRS process and health/wellbeing role.

Will present to SENP on this piece of work to share lessons learned.

- Discussion: Biodiversity Opportunity Areas

Understanding the relationship between BOAs and LNRS.

Discussion

In several local plans/strategies, there is a policy that relates specifically to BOAs. 97% of BOAs are still valuable and there is the potential to expand some of these.

LNRS will be material consideration in planning but importance between LNRS and BOAs unclear. BOAs are also potentially important for BNG so there needs clarity over that too.

Incorporate BOAs as a strand of work within the production of LNRS to keep them relevant.

Defra state that LNRSs won’t cover everything. BOAs (+other strategies) will also be important.

- AOB

First ADC LP direction of travel document is out for consultation, finishes on 13th May 5pm.

- DONM

  - Next meeting on 05/06/2024